## Dashboard
PROJECT REPORTING DASHBOARD
DATE | TOTAL ITERATION | 2 | SPRINT 1 START DATE | ITERATION DURATION | 1.5 days | SPRINT 2 START DATE | Team Size
Note:- To view the Burndown chart for a particular day the next day should be selected in the Sprint Progress dropdown. For viewing the complete Sprint Burndown chart the status should be set to completed in the dropdown

## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | User Story Point | Assignee | Status
1 | 1 | US-1 | User Registration: As a user: I want to register to the application with full name, username, email and password. This microservice will be responsible for user authentication and managing user profile. It will provide APIs for user registration, authentication, and updating user profiles. | MUST HAVE | 3 | Utkarsh | 3- Completed
1 | 1 | US-2 | User Login: As a user: I want to login with registered credentials | MUST HAVE | 3 | Utkarsh | 3- Completed
1 | 1 | US-3 | View and Like post: As a user: I can view and like the posts.This microservice will manage posts which include posting text, photos, and videos and viewing and liking posts shared by others | MUST HAVE | 8 | Utkarsh | 3- Completed
1 | 1 | US-4 | Following users: As a user: I can follow other users and other people can follow me. This microservice is responsible for managing the followers. It will provide APIs for following other users, getting the profiles of followers, and a list of followers | MUST HAVE | 8 | Utkarsh | 3- Completed
1 | 1 | US-5 | Search specific users/tag: As a User: I can search for other users and tags | MUST HAVE | 13 | Utkarsh | 3- Completed
1 | 1 | US-6 | Delete post: As a user: I can delete my own post | COULD HAVE | 5 | Utkarsh | 3- Completed
1 | 1 | US-7 | Exploring trending contents: As a user: I can view the trending contents on the platform. This microservice will provide APIs that will help to fetch the trending posts with real-time updates | MUST HAVE | 21 | Utkarsh | 3- Completed
Note on F1: Kindly refrain from providing more than 8 points to user stories

## Sprint I Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
[8 empty] | 95 | 49 | 18 | 13 | 8 | 3 | 1
SPRINT 1 BACKLOG
US-1 | T1 | Analysis | 2024-02-28 | 2024-02-28 | Utkarsh | General | 3- Completed | 8 | 5 | 3 | 0 | 0 | 0 | 0
| T2 | Authentication Service Backend Basics | 2024-02-29 | 2024-02-29 | Utkarsh | Coding | 3- Completed | 10 | 5 | 2 | 1 | 1 | 1 | 0
| T3 | User Registerations | 2024-02-29 | 2024-02-29 | Utkarsh | Coding | 3- Completed | 10 | 5 | 2 | 2 | 1 | 0 | 0
US-2 | T1 | Login Analysis | 2024-03-01 | 2024-03-02 | Utkarsh | General | 3- Completed | 5 | 4 | 1 | 0 | 0 | 0 | 0
| T2 | Login | 2024-03-01 | 2024-03-02 | Utkarsh | Coding | 3- Completed | 6 | 4 | 0 | 0 | 0 | 0 | 0
US-3 | T1 | Analysis | 2024-02-28 | 2024-02-29 | Utkarsh | General | 3- Completed | 5 | 4 | 0 | 0 | 0 | 0 | 0
| T2 | Object Storage Service | 2024-03-03 | 2024-03-04 | Utkarsh | Coding | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0
| T3 | Post Microservice Design | 2024-03-05 | 2024-03-05 | Utkarsh | Coding | 3- Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0
| T4 | Post Implementation | 2024-03-06 | 2024-03-06 | Utkarsh | Coding | 3- Completed | 5 | 1 | 1 | 1 | 1 | 0 | 0
US-4 | T1 | Analysis | 2024-02-28 | 2024-02-29 | Utkarsh | General | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0
| T2 | Follow Microservice | 2024-03-07 | 2024-03-07 | Utkarsh | Coding | 3- Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0
US-5 | T1 | Analysis | 2024-02-28 | 2024-02-29 | Utkarsh | General | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0
| T2 | User Feed Microservice | 2024-03-08 | 2024-03-08 | Utkarsh | Coding | 3- Completed | 10 | 3 | 3 | 3 | 1 | 1 | 1
US-6 | T1 | Analysis | 2024-02-28 | 2024-02-29 | Utkarsh | General | 3- Completed | 5 | 4 | 0 | 0 | 0 | 0 | 0
| T2 | Trending Implementation in User feed service | 2024-03-09 | 2024-03-09 | Utkarsh | Coding | 3- Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work

## Sprint II Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day1 | Day2 | Day3
[8 empty] | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-01 | T1 | Design of UI (Wire Frame)
| T3 | Managing source code with Git & publishing final build using Maven
| T4 | Consuming The Exposed WebService from the Existing App
| T5 | Repurposing and Filtering the Data according to new requirement
| T6 | Exposing the Repurposed data by creating a new WebService(API) class
| T7 | Consuming the Webservice by using an Angular Client
| T8 | Unit testing
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work

## Stand up Meeting
Sprint | US ID | Day | Assigned To | Points Discussed | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken

## Reference Data
SPRINT I BURN-DOWN CHART DATA
Sprint | Day | Planned | Actual | TEAM VELOCITY CHART
1 | 0 | 95 | 67
| 1 | 63.33 | 49 | Sprint | Planned | Actual
| 2 | 31.66 | 18 | 1 | 95 | 67
| 3 | 10.55 | 0 | 2 | 0 | 0
SPRINT II BURN-DOWN CHART DATA
Sprint | Day | Planned | Actual
2 | 1 | 0 | 0
| 2 | 0 | 0
| 3 | 0 | 0
| 4 | 0 | 0
Note on E6: Effort hours pending after day 1 of sprint 1
Note on E7: Effort hours pending after day 2 of sprint 1
Note on H7: Planned hours of effort in Sprint 1
Note on I7: Story points completed in sprint 1
Note on H8: Planned hours of effort in Sprint 2
Note on I8: Story points completed in Sprint 2
Note on E15: Effort hours pending after day 1 of sprint 2
Note on E16: Effort hours pending after day 2 of sprint 2